City of Toronto

Long-Term Care Homes & Services

2023 Capital Maintenance Plan

Cummer Lodge

MoHLTC Review Submission

November 2023

Moshsha Charles

Manager, Building Services, Cummer Lodge

Seniors Services and Long-Term Care

City of Toronto

205 Cummer Ave,

North York, ON, M2M 2E8

Tel: 416-392-9506

Moshsha.Charles@toronto.ca

Table of Contents

- Project Summary

  - Maintenance Projects Overview

  - Flooring Replacement – Detailed Description

- Operational Plan

  - Overview of Project

  - Administration

  - Communication

  - General Safety Measures

  - Resident Home Areas (RHA)

  - Kitchen/Food Service

  - Laundry Services

  - Waste Disposal

  - Noise Factors

  - After Hours Work

  - Staff Work Space

  - Summary

        - Project Summary

- Existing Home

Cummer Lodge, located in North York, is a Long-Term Care home operated by the City of Toronto and home to 391 residents.

As part of an annual capital maintenance plan, the City plans to conduct several repairs and upgrade projects in order to modernize the facility, and keep the building and grounds in a state of general good repair.

The 2023 Capital Maintenance Plan for Cummer Lodge includes:

- Flooring Replacement:

- Vinyl composite tile and vinyl sheet flooring replacement on 2nd level North Wing;

Work is to begin following Ministry approval of the plans and completion of the City of Toronto tendering process. It is anticipated that the project will take approximately 3 months to complete after the contract is awarded.

- Flooring Replacement – Detailed Description

The purpose of this project is to

        - replace damaged and worn existing vinyl composite tile flooring and wall base in the following areas:

- Second floor – North Wing

- Corridors, Activity room, Kitchen, TV Lounge, Family & Resident Lounge

- Read room, Lift Room

- Soiled & Clean Utility, Storage, HSKP, Electrical Closet

- Shower and Tub rooms (N220, N255)

- Nurse’s Stations, Charting, Medical Supply, Nurse Manager, Staff Washroom

- All resident Rooms & en-suite washrooms

- Dining Room (N225, N226, N227) - included as an Alternative Price, may not be proceeded.

        - replace Corner guards in all listed above rooms - included as an Alternative Price, may not be proceeded.

2) Operational Plan

- Overview of Project

Phasing

The maintenance project will have several disruptions to the operation of the home, due to restricting the usable area of flooring. To minimize disruptions, a detailed phasing plan will be required, please see “Special Considerations”.

Permits/Approvals

Flooring replacement project will not require building permits.

Hours of Work

Work will take place during regular working hours as defined in the Project Specification and as determined by the Supervisor of Building Services. Unless otherwise specified, hours of work will be standard, between 8am and 5pm.

Anticipated Timelines

The project is estimated to take 6 months to complete. All work will be completed within the 2024 calendar year.

Special Considerations

Contractor will coordinate area of work with Home.

Resident Services Manager will plan and oversee all resident activities.  Resident activities will be relocated to a suitable location depending on daily scheduled work.

Construction and demolition in corridors shall be coordinated to reduce the impact the general day to day function of the home. The condition of the flooring replacement shall be made good at the end of each day such that staff and residents can maintain normal use of the facilities.
The Contractor shall maintain access to one shower/tub room and two washrooms per resident zone at all times for the duration of work in the above outlined areas.

Environmentally friendly, low odour glue will be exclusively used to protect the health of residents and staff.

- Administration

The home’s Administer will be assisted during this project by the home's staff particularly Manager of Building Services. The Architect for the project is Montgomery Sisam Architects Inc. The City of Toronto’s Head Office Project Manager will also manage the Owner’s responsibilities.

In order to facilitate effective and timely communication the following protocols will be in-place:

- Morning meetings with the Administrator or delegate.

- Administrative rounds with the Supervisor Building Services and union co-chair of the OH&S Committee as required.

- Communication

Before construction begin, a start-up meeting / orientation will be held with the Contractor and home staff, outlining the requirements imposed on Contractors working in a Long-Term Care environment, and protocols that the Contractor will be expected to follow.  All issues with respect to both resident and staff safety will be identified with staff involvement and will be communicated though formal and informal meetings.

- The Residents’ Council as well as residents and families will be informed of the maintenance projects, expected completion dates and any contingency plan if required.

- All staff will be informed and communicated via general staff meetings and departmental meetings.

- The Administrator or delegate will notify the Ministry of Health and Long-Term Care Regional Office when work is about to begin.

- General Safety Measures

Name of person assigned to monitor safety:

Moshsha Charles, Manager, Building Services

All areas of work will be separated from building users and visitors using barricades and/or hording as required as to the satisfaction of the Building Services Manager and the Architect.

Each area will be cleaned of debris and construction material frequently during each day and thoroughly cleaned at shift end.

- Barriers / Tool and Equipment Storage

The Contractor must provide temporary measures to ensure all work areas, for all projects, are secure from residents between all working areas and resident spaces.  Dust protection must be incorporated to protect residents and resident spaces from dust exposure.  Tools and equipment must be not be left in areas accessible to residents and must be locked in a secure location when unattended. All tools and equipment shall be stored in a secured location as coordinated with the Building Service Manager.

- Alarms

All door alarms, fire alarms and nurse call devices will operate normally in all areas of the home during the renovation period. Should it be necessary to temporarily bypass a fire zone, a manual fire watch will be implemented.  All fire zones will be restored to full operation at the end of each construction day.

- Housekeeping / Cleanliness

The Contractor shall keep all construction areas clean of construction debris and waste throughout the day.  Housekeeping routines will be adjusted to maintain an acceptable level of cleanliness.  Housekeeping hours will be adjusted, if required, to keep up with the increased demand.

- Transporting Construction Materials

Construction deliveries will be delivered to specific area as coordinated with the Building Service Manager.  All materials that are to be transported throughout the building shall be transported by routes as informed by the Building Service Manager. If required to transport goods and equipment to floor levels not accessible from grade level, the Contractor shall use a dedicated elevator and must coordinate with the home timelines for elevator use to cause minimal disturbances to the home.

- Resident Home Areas (RHA)

3-4 resident’s rooms and en-suite washrooms flooring replacement shall be completed per day with the resident returned to their room by the end of day. There will be no overnight work in resident rooms.

To ensure privacy and safety and safety of care:

- Residents in rooms under construction will be relocated within their own unit as deemed necessary during the renovation, with minimal disruption to the residents.

- Rest areas will be located on the unit in available lounges, residents beds will be relocated as per daily scheduled work with appropriate privacy screens.

- The Nurse Manager will be on site at all times with regular rounds by DOC & the administrator.

- Kitchen/Food Service

It is anticipated that food service disruption will be minimal.

- Work in the dining room to be done afterhours to mitigate disruption,

- All food service deliveries will not be affected. Delivery of meals to the units will not be affected.

- Laundry Service

No impact on laundry service throughout the facility.

- Waste Disposal

Contractor to put a waste bin within the loading area of Long-Term Care Home. Contractor should erect a signage to make sure no mixing on construction and home waste.

- Noise Factors

All reasonable measure will be taken to reduce noise.

Project work will take place during the normal business hours of 8 a.m. to 5 p.m.

- After Hours Work

It is anticipated there will be afterhours work required for dining room floor replacement. There will be no afterhours work in resident rooms and directly adjacent corridors.

- Staff Work Space

It is anticipated that there will be minimal impacts on staff work space. Nurse stations and dining room on the fourth floor should be comprehensively scheduled with the home for either after hours or normal hours work to mitigate disruptions on staff working spaces.

- Summary

The work outlined in this operational plan will require co-ordination and communication between the Contractor and the Home to ensure the planned improvements are achieved with minimal impact to residents.

When preparing this Operational Plan an emphasis was placed on the resident and staff's comfort and safety. This plan works to minimize impact on the daily lives of the people living and working at each Home by holding Contractors to their schedules and maintaining clear lines of communication between all staff members, residents and families.