City of Toronto

Long-Term Care Homes & Services

2024 Capital Maintenance Plan

Seven Oaks

MoHLTC Review Submission

January 2024

Home Contact

Diana Godlewski, 
Manager, Building Services, Seven Oaks

City of Toronto Long Term Care Homes & Services

9 Neilson Road

Scarborough, ON M1E 5E1

416-392-3518

diana.godlewski@toronto.ca

Table of Contents

- Project Summary

  - Maintenance Projects Overview

  - Servery and Pot Wash Upgrades – Detailed Description

  - Resident En-suite Washroom Sliding Doors Replacements – Detailed Description

  - Resident Room Flooring Replacement – Detailed Description

- Operational Plan

  - Overview of Project

  - Administration

  - Communication

  - General Safety Measures

  - Emergency Plan / Life Safety Plan

  - Resident Home Areas (RHA)

  - Food Service

  - Waste Disposal

  - Noise Factors

  - After Hours Work

  - Staff Work Space

  - Summary

        - Project Summary

- Maintenance Project Overview

Seven Oaks is a 249-bed, Long-Term Care Home operated by the City of Toronto that has been serving the community of Scarborough since 1989.

As part of an annual capital maintenance plan, the City plans to conduct several repairs and upgrade projects in order to upgrade and modernize the facility, and keep the building and grounds in a state of general good repair.

The 2023 Capital Maintenance Plan for Seven Oaks includes:

- Upgrade Serveries at Level 4 and Pot Wash area in the Basement level

- Replacement of sliding doors in resident’s ensuite washrooms on Level 3.

- Replacement of existing flooring in first-floor resident’s rooms.

Work is to begin following Ministry approval of the plans and completion of the City of Toronto tendering process.

- Project Summary

2.a	Servery and Pot Wash Upgrades – Detailed Description

To provide an improved environment for staff and residents, elements of the food delivery system at Seven Oaks will be renovated. Staff areas of the existing serveries have poor ergonomics, damaged and difficult to clean surfaces, combined with insufficient storage. The resident-facing areas of the serveries are heavily worn with dated finishes. The basement level pot wash area is a heavy traffic zone with poor ventilation and inefficient equipment configuration.

The purpose of the project is to:

- Upgrade Servery at Level 4 – allowing for better work flow;

- Replace flooring under the existing counters and in the servery area;

- Upgrade Pot Wash area in the Basement Level

- Install new exhaust in Pot Wash for improved ventilation;

- Create a new Cart Wash adjacent to Pot Wash.

2.b	Resident Washroom Sliding Door Replacements – Detailed Description

The purpose of this project is to replace the damaged and worn sliding doors in the resident ensuite washrooms on Levels 3. After three decades of heavy use the doors are at their end of life. New doors will be sturdy, easily cleanable, with replaceable edges to provide longevity. New sliding doors tracks will provide smooth and quiet operation. In total 42 doors will be replaced on 3rd floor.

Work includes:

- Removal of existing sliding doors, valance, tracks and floor guides.

- Patching, painting and repair of all surfaces impacted by demolition.

- Installation of new sliding doors, door tracks, floor guides, valance and frame protection.

2.c	Resident Room Flooring Replacement - Detailed Description

The purpose of this project is to replace damaged and worn existing vinyl composite tile flooring and wall base in the resident rooms and en-suite washrooms on first floor to suit latest IPAC standards of a monolithic sheet flooring with heat welded seams.

Work includes:

•	Removal of existing corner guards, vinyl composite tile, wall base and vinyl sheet flooring in resident’s room and en-suite washroom respectively.

•	Patching, painting and repair of all surfaces impacted by demolition.

•	Installation of new corner guards, flooring and wall base.

Operational Plan

- Overview of Project

Phasing

All work within Pot wash and Servery at Level 4 project will be comprehensively scheduled with the Home prior to start-up onsite. Contractor will be required to adhere to this schedule for the duration of the work. All Phasing will be subject to approval from the Building Services Manager and as identified in the Ministry of Health Operational Plan for the Work. Contractor will be required to phase work associated with loading dock and service elevator to minimize disruption to the Home operation.

Work involving the Resident En-suite Washroom Sliding Doors and Resident flooring replacement will require phasing. Contractor can only intervene in so many rooms as not to impact home operations and ensure resident room can be occupied at the end of the day. Maximum 4 rooms could be completed per day. To minimize disruptions, all work within this project will be comprehensively scheduled with the Home prior to start-up on site. Contractors will be required to adhere to this schedule for the durations of the work. Refer to Special Considerations and Section 5- Resident Home Area for additional information.

Permits/Approvals

Pot wash and Servery at Level 4 project will require a building, electrical and plumbing permit. All permits will be acquired prior to the commencement of work.

Resident Washroom Sliding Door Replacements project will not require building permit.

Resident Room Flooring Replacement project will not require building permit.

Hours of Work

Work will take place during regular working hours as defined in the Project Specification and as determined by the Supervisor of Building Services. Unless otherwise specified, hours of work will be standard, between 8am and 5pm.

Any work associated with loading dock and service elevator to be scheduled between 1:30pm and 5pm and confirmed with the Home to minimize disruption to the Home operation.

Anticipated Timelines

Construction window assumed to be 6 months. Work is to begin following Ministry approval of the plans and completion of the City of Toronto tendering process. 


Special Considerations

The maintenance projects will have several impacts to the operation of the home due to work in the basement pot wash and Level 4 servery. The pot wash area at the basement will be affected during construction, other dish wash area will be arranged within the home to minimise impact. Loading area, holding area and service elevator will be affected, the construction periods will be coordinated with the Home. Temporary servery to be established within the existing dining room at Level 4.

The maintenance projects will have several impacts to the operation of the home due to work in 1st and 3rd floor resident suites. To minimize disruptions, all work within this project will be comprehensively scheduled with the Home prior to start-up on site. Contractors will be required to adhere to this schedule for the durations of the work.

Schedule will be posted and reviewed with care team in advance to ensure appropriate measures are in place to support residents that are displaced for up to 8 hours during the work. Measures may include additional programs, support staff and/or PCA's depending on resident care needs. Contractor will do their best to minimize noise disruption by ensuring room doors are kept closed while work is being completed.

- Administration

The home’s Administrator will be assisted during this project by the home's staff particularly Manager of Building Services. The Architect for the project is Montgomery Sisam Architects Inc. The City of Toronto’s Head Office Project Manager will also manage the Owner’s responsibilities.

In order to facilitate effective and timely communication the following protocols will be in-place:

- Morning meetings with the Administrator or delegate.

- Administrative rounds with the Supervisor Building Services and union co-chair of the OH&S Committee as required.

- Communication

Before construction begin, a start-up meeting / orientation will be held with the Contractor and home staff, outlining the requirements imposed on Contractors working in a Long-Term Care environment, and protocols that the Contractor will be expected to follow.  All issues with respect to both resident and staff safety will be identified with staff involvement and will be communicated though formal and informal meetings. The Home will provide an orientation –training date for the Contractor prior to the start of the project.

- The Residents’ Council as well as residents and families will be informed of the maintenance projects, expected completion dates and any contingency plan if required.

- All staff will be informed and communicated via general staff meetings and departmental meetings.

- The Administrator or delegate will notify the Ministry of Health and Long-Term Care Regional Office when work is about to begin.

- General Safety Measures

Name of person assigned to monitor safety: 
Diana Godlewski, Manager, Building Services & the JOHSC team

All areas of work will be separated from building users and visitors using barricades and/or hording as required as to the satisfaction of the Building Services Manager and the Architect.

Each area will be cleaned of debris and construction material frequently during each day and through cleaning at shift end.

- Barriers / Tool and Equipment Storage

The Contractor must provide temporary measures to ensure all work areas, for all projects, are secure from residents between all working areas and resident spaces.  Dust protection must be incorporated to protect residents and resident spaces from dust exposure.  Tools and equipment must not be left in areas accessible to residents and must be locked in a secure location when unattended. All tools and equipment shall be stored in a secured location as coordinated with the Building Service Manager.

- Alarms

All door alarms, fire alarms and nurse call devices will operate normally in all areas of the home during the renovation period. Should it be necessary to temporarily bypass a fire zone, a manual fire watch will be implemented.  All fire zones will be restored to full operation at the end of each construction day.

- Water Shutoff

It is not anticipated that any building water shut-offs will be required for this project – only localized. If required Contractor will need shut-off water that affects residents, 48 hours’ notice will need to be provided. Any water-shut off affecting residents (if required) will only be during the day and to be minimized as much as possible.

- Housekeeping / Cleanliness

The Contractor shall keep all construction areas clean of construction debris and waste throughout the day.  Housekeeping routines will be adjusted to maintain an acceptable level of cleanliness.  Housekeeping hours will be adjusted, if required, to keep up with the increased demand.

- Transporting Construction Materials

Construction deliveries will be delivered to specific area as coordinated with the Building Service Manager.  All materials that are to be transported throughout the building shall be transported by routes as informed by the Building Service Manager. If required to transport goods and equipment to floor levels not accessible from grade level, the Contractor shall use a dedicated elevator and must coordinate with the home timelines for elevator use to cause minimal disturbances to the home.

- Emergency Plan / Life Safety Plan

In general, this work does not affect the overall supply of electricity or natural gas to the home.  Although work on this project should not cause a disruption to any essential services, if such a disruption were to occur the home Emergency Measures Plan would be put into effect.  The plan has measures that compensate for loss of essential services.

In order to ensure the smooth implementation of the Emergency Measures Plan, the Administrator, Assistant Administrator and the Manager Building Services will review the plan and become comfortable with it before work commences on this project.

- Resident Home Areas (RHA)

Pot wash area in the Basement and Servery at levels 4:

- Any impact on areas with Residents (if required) will be planned and overseen by the Resident Services Manager.  Resident activities will be relocated to a suitable location on the unit depending on daily scheduled work

Resident En-suite Washroom Sliding Door Replacements and Flooring replacements:

- All resident suites on Level 3 and Level 1 will be impacted by the sliding door replacement and flooring replacement project. It is anticipated that 4 to 6 suites will be worked on per day for ensuite door replacement and 2 suites per day for flooring replacement.

- Residents of suites under construction will be temporarily relocated within their RHA. All work in resident suites is to be fully completed by the end of the day, allowing residents to return to their rooms, and requiring no overnight relocation.

- A rest area will be provided for temporarily relocated residents. Location coordinated with Home.

- Resident’s access to washrooms facilities located within the RHA will not be impacted.

- Food Service

The Food and Nutrition department will be affected during the Pot wash and Servery at Level 4 project. Mealtimes will be maintained. During construction, temporary servery will be established within the existing dining rooms. Food will be brought in hot food carts for service to residents.
There will be no interruption to daily mealtime services provided.
There is no anticipated impact on meal delivery to resident rooms.

Construction work will not be allowed during meal times.

- Waste Disposal

The contractor for the duration of the project will have a waste bin adjacent to the waste disposal area. Location for waste bin will be coordinated with the home to mitigate operational impacts. There will be temporary hoarding erected to accommodate exhaust duct installation within the plenum spaces above the loading dock, times for hoarding will be coordinated with all deliveries and pick ups.

- Noise Factors

All reasonable measure will be taken to reduce noise. Construction will take place during normal business hours of 8:00 a.m. to 5:00 p.m.  Highest noise levels will be contained in the hoarded areas.  All efforts will be made to schedule resident activities in other areas of the Home to minimize any impact of noise on the residents. Any work requiring extensive drilling will be scheduled with the home. Contractor shall give the Home 72 hours’ notice prior to any noise and vibration-associated work.

- After Hours Work

The Contractor will be required to conduct after hours work to disrupt the service elevator at the basement level to accommodate installation of exhaust duct work. The timing of any required work will be coordinated to minimize the impact to residents. All afterhours work shall be at the approval of the Manager of Building Services.

- Staff Work Space

During construction in the basement Pot Wash area the existing sink will continue to be in service. Where new work is to be done the area will be completely hoarded during renovation thereby ensuring safety while minimizing dust exposure.

- Summary

The work outlined in this operational plan will require co-ordination and communication between the Contractor and the Home to ensure the planned improvements are achieved with minimal impact to residents.

When preparing this Operational Plan an emphasis was placed on the resident and staff's comfort and safety. This plan works to minimize impact on the daily lives of the people living and working at each Home by holding Contractors to their schedules and maintaining clear lines of communication between all staff members, residents and families.